## Mass
Mass Report
Resource | Expected Weight (g) | Measured Weight (g) | Uncertainty (%) | Margin (±g)
Battery | 4.1 |  | 15% | 0.6
Accelerometer (ADXL345) | 1.27 |  | 31% | 0.4
MCU+Blutetooth Module | 2 |  | 20% | 0.4
EDA Sensor/Electrodes | 10 |  | 30% | 3
32 kHz RTC | 0.05 |  | 10% | 0.005
3D Printing | 50 |  | 30% | 15
PCB | 3 |  | 10% | 0.3
Project Allocation | (L2 Requirements) |  |  |  | 72
Total Margin |  |  |  |  | 19.705
Total Expected Weight |  |  |  |  | 70.42
Contingency |  |  |  |  | 21.285

## Power
Power Report
Resource | Expected Current Draw (mA) | Measured Current Draw (mA) | Uncertainty (%) | Margin (±mA)
Accelerometer (ADXL345) | 0.035 |  | 10% | 0.004
MCU+Blutetooth Module | 4.5 |  | 10% | 0.45
EDA Sensor/Electrodes | 0.02 |  | 10% | 0.002
32 kHz RTC | 0.00039 |  | 5% | 1.8e-08
Project Allocation | 100mAh (1 hr for Level 1 Requirement with chosen battery) |  |  |  | 100
Total Margin |  |  |  |  | 0.456
Total Expected Current |  |  |  |  | 4.5554
Contingency |  |  |  |  | 95.9006

## Cost
Cost Report
Resource | Expected ($) | Measured ($) | Uncertainty (%) | Margin (±$)
Battery | 3.6 |  | 10% | 0.36
Accelerometer (ADXL345) | 17.5 |  | 20% | 3.5
MCU+Blutetooth Module | 8.03 |  | 3% | 0.24
EDA Sensor/Electrodes | 9.9 |  | 5% | 0.5
32 kHz RTC | 1.5 |  | 10% | 0.15
3D Printing | 4.33 |  | 80% | 3.46
PCB | 5 |  | 10% | 0.5
Shipping | 35 |  | 20% | 7
Project Allocation |  |  |  |  | 350
Total Margin |  |  |  |  | 15.71
Total Expected |  |  |  |  | 84.86
Contingency |  |  |  |  | 280.85