## Sheet1
Tasks | % Needed | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13 | Week 14 | Week 15 | Week 16
Define Objectves | 1 | 1 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
L1 Requirements | 1 | 1 | 0.9 | 0.8 | 0.6 | 0.4 | 0.3 | 0.2 | 0.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Create Schedule | 1 | 1 | 1 | 1 | 1 | 0.8 | 0.2 | 0.1 | 0.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Manage Schedule | 1 | 1 | 0.93333 | 0.86667 | 0.8 | 0.73333 | 0.66667 | 0.6 | 0.53333 | 0.46667 | 0.4 | 0.33333 | 0.26667 | 0.2 | 0.13333 | 0.066667 | 0
Create Budget | 1 | 1 | 1 | 0.8 | 0.6 | 0.4 | 0.2 | 0.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WBS | 1 | 1 | 1 | 1 | 0.8 | 0.4 | 0.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PDD | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PPP | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PDR | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CDR | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0
Final Documentation | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
Project Video | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
Manage Budget | 1 | 1 | 1 | 1 | 0.9 | 0.8 | 0.7 | 0.6 | 0.5 | 0.4 | 0.3 | 0.25 | 0.2 | 0.15 | 0.1 | 0.5 | 0
Mission | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
L2 Requirements | 1 | 1 | 0.8 | 0.6 | 0.4 | 0.2 | 0.15 | 0.1 | 0.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
System Block Diagram | 1 | 1 | 1 | 0.5 | 0.3 | 0.2 | 0.1 | 0.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PBS | 1 | 1 | 1 | 0.5 | 0.3 | 0.2 | 0.1 | 0.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Interface Definition | 1 | 1 | 1 | 0.6 | 0.5 | 0.45 | 0.4 | 0.35 | 0.3 | 0.25 | 0.2 | 0 | 0 | 0 | 0 | 0 | 0
Cable Tree | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0.8 | 0.6 | 0.4 | 0.2 | 0 | 0 | 0 | 0 | 0
Power Report | 1 | 1 | 1 | 1 | 1 | 0.8 | 0.6 | 0.5 | 0.4 | 0.3 | 0.2 | 0.15 | 0 | 0 | 0 | 0 | 0
Mass Report | 1 | 1 | 1 | 1 | 1 | 0.8 | 0.6 | 0.5 | 0.4 | 0.3 | 0.2 | 0.15 | 0 | 0 | 0 | 0 | 0
Control Panel Customization | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0.8 | 0.6 | 0.4 | 0 | 0 | 0 | 0 | 0 | 0
Android Application | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0.8 | 0.6 | 0.4 | 0 | 0 | 0 | 0 | 0 | 0
FOV for Camera | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0.6 | 0.3 | 0.1 | 0 | 0 | 0 | 0 | 0 | 0
RC Mode | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0.8 | 0.6 | 0.4 | 0.2 | 0.2 | 0 | 0 | 0 | 0
Verification Test Plan | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0.8 | 0.8 | 0.6 | 0.4 | 0.2 | 0
Verification Matrix | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0.8 | 0.8 | 0.6 | 0.4 | 0.2 | 0
Verification Test | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
Verification Report | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
L2 Sub-requirements | 1 | 1 | 0.8 | 0.6 | 0.4 | 0.2 | 0.15 | 0.1 | 0.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Motor Specification | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sensor Specification | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sensor FOV | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0.9 | 0.6 | 0.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Trade-off Motor | 1 | 1 | 1 | 1 | 1 | 0.7 | 0.5 | 0.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Trade-off Sensor | 1 | 1 | 1 | 1 | 1 | 0.7 | 0.5 | 0.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sensors on Model | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0.8 | 0.6 | 0.4 | 0.2 | 0
Motor on Model | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0.7 | 0.4 | 0.3 | 0.2 | 0.1 | 0 | 0 | 0
Rapid Prototyping (CDR) | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0.7 | 0.5 | 0.3 | 0.2 | 0 | 0 | 0 | 0 | 0
Rapid Protyping (PDR) | 1 | 1 | 1 | 1 | 1 | 1 | 0.4 | 0.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Fritzing Diagram Sensor | 1 | 1 | 1 | 1 | 1 | 0.7 | 0.5 | 0.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Fritzing Diagram PCB | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0.7 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0
Breadboard Schematic Sensor | 1 | 1 | 1 | 1 | 1 | 0.7 | 0.5 | 0.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Breadboard Schematic PCB | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0.7 | 0.4 | 0 | 0 | 0 | 0 | 0 | 0
Schematic Eagle CAD | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0.7 | 0.4 | 0 | 0 | 0 | 0 | 0 | 0
Test PCB | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
Test 3Dot Board | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PCB Component Specification | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0.6 | 0.3 | 0.1 | 0 | 0 | 0 | 0 | 0
Purchase Motor | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Purchase Sensors | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Code for navigation | 1 | 1 | 1 | 1 | 1 | 1 | 0.8 | 0.6 | 0.55 | 0.5 | 0.4 | 0.3 | 0.25 | 0.1 | 0.5 | 0.5 | 0
Code for Speakers | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0.9 | 0.7 | 0.4 | 0.3 | 0.2 | 0 | 0 | 0
Code for LEDS | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0.7 | 0.5 | 0.4 | 0.3 | 0.2 | 0 | 0 | 0
Purchase Battery | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
L2 Sub-requirements | 1 | 1 | 0.8 | 0.6 | 0.4 | 0.3 | 0.25 | 0.2 | 0.15 | 0.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mechanical Interface Design | 1 | 1 | 1 | 1 | 0.8 | 0.6 | 0.4 | 0.3 | 0.2 | 0.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Simulation | 1 | 1 | 1 | 1 | 0.9 | 0.8 | 0.6 | 0.4 | 0.3 | 0.2 | 0.1 | 0 | 0 | 0 | 0 | 0 | 0
Model PDR | 1 | 1 | 1 | 1 | 1 | 1 | 0.5 | 0.1 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
Model CDR | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0.8 | 0.6 | 0.3 | 0 | 0 | 0 | 0 | 0 | 0
Stress Analysis | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0.8 | 0.5 | 0.3 | 0 | 0 | 0 | 0 | 0 | 0
Displacement Analysis | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0.8 | 0.5 | 0.3 | 0 | 0 | 0 | 0 | 0 | 0
Strain Analysis | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0.8 | 0.5 | 0.3 | 0 | 0 | 0 | 0 | 0 | 0
SMT Stencil | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0.5 | 0.5 | 0 | 0 | 0
Solder PCB | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
Purchase PCB and Parts | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
PCB Layout | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0.8 | 0.5 | 0.3 | 0.2 | 0.1 | 0 | 0 | 0 | 0
Solder 3Dot Board | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3D Model of Goliath | 1 | 1 | 1 | 0.92857 | 0.85714 | 0.78571 | 0.71429 | 0.64286 | 0.57143 | 0.5 | 0.42857 | 0.35714 | 0.28571 | 0.21429 | 0.14286 | 0.071429 | 0
3D Print Goliath | 1 | 1 | 1 | 1 | 1 | 0.91667 | 0.83333 | 0.75 | 0.66667 | 0.58333 | 0.5 | 0.41667 | 0.33333 | 0.25 | 0.16667 | 0.083333 | 0
Purchase Tracks | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Pruchase Periscope | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Purchase Small Ports | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0.8 | 0.6 | 0.4 | 0.2 | 0.1 | 0 | 0 | 0 | 0 | 0
Purcahse Wires | 1 | 1 | 1 | 1 | 1 | 1 |  | 1 | 1 | 1 | 1 | 1 | 1 | 0.7 | 0.3 | 0.1 | 0
3D Model Wires | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0.7 | 0.3 | 0.1 | 0
Assemble | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
Ideal Done | 73 | 75 | 70 | 65 | 60 | 55 | 50 | 45 | 40 | 35 | 30 | 25 | 20 | 15 | 10 | 5 | 0
Reality Done | 73 | 73 | 72.2333 | 69.7952 | 67.5571 | 61.5857 | 52.0643 | 43.9429 | 37.5714 | 31.2 | 25.6286 | 20.1571 | 16.3357 | 14.1143 | 8.8429 | 8.0214 | 0

## Sheet2
Define Objectves
L1 Requirements
Create Schedule
Manage Schedule
Create Budget
Manage Budget
WBS
PDD
PPP
PDR
CDR
Final Documentation
Project Video
Project Binder
Mission Success
Systems
System Design
L2 Requirements
System Block Diagram
PBS
Interface Definition
Cable Tree
Mass Report
Power Report
Software
Control Panel Customization
Android Application
FOV for Camera
RC Mode
Software Block Diagram
Systems Test
Verification Test Plan
Verification Matrix
Verification Test
Verification Report
Electronics
Electronic Design
L2 Sub-requirements
Motor Specificication
Sensor Specification
Experiments
Trade-off Motor
Trade-off Sensor
Sensor FOV
Rapid Prototype (PDR)
Rapid Prototype (CDR)
Control Algorithm
Running Averager
Sensors on Model
Motor on Model
Microcontroller
Fritzing Diagram
Breadboard Schematic
Schematic Eagle CAD
Test PCB
PCB Component Specification
Test 3Dot Board
Control
Purchase Motor
Purchase Sensors
Code for navigation
Power
Battery from Spring 2016
Manufacturing
Mechanical Design
L2 Sub-requirements
Mechanical Interface Design
Experiments
Simulation of Model
Model PDR
Compare Idle vs Rotating Wheels
Static
Drop Test
Motion Study Test
Model CDR
PCB Layout
SMT Stencil
Solder PCB
PCB Layout
Purchase PCB
Solder 3Dot Board
3D Modeling
Goliath
Component Manufacturing
3D Print Goliath
Purchase Tracks
Purchase Periscope
Purchase Small Parts
Wiring Harness
Purchase Wires
3D model
Goliath Buildout
Assemble