## Project Planner
Project Planner
| Select a period to highlight at right. A legend describing the charting follows. |  |  |  |  | Period Highlight: | 1 |  |  | Plan Duration | [5 empty] | Actual Start |  |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (with time extension)
Ed = Green
|  | Ed = Green | Ray = Blue | Kris = Purple | ALL = Brown |  | January | [9 empty] | Feburary | [27 empty] | March | [30 empty] | April | [29 empty] | May
[8 empty] | 23rd |  | 25th |  |  |  |  | 30th |  | 1st |  |  |  |  | 6th |  | 8th |  |  |  |  | 13th |  | 15th |  |  |  |  | 20th |  | 22nd |  |  |  |  | 27th |  | 1st |  |  |  |  | 6th |  | 8th |  |  |  |  | 13th |  | 15th |  |  |  |  | 20th |  | 22nd |  |  |  |  | 27th |  | 29th |  |  |  |  | 3rd |  | 5th |  |  |  |  | 10th |  | 12th |  |  |  |  | 17th |  | 19th |  |  |  |  | 24th |  | 26th |  |  |  |  | 1st |  | 3rd |  |  |  |  | 8th |  | 10th |  |  |  |  | 15th |  | 17th | 18th
| ACTIVITY | PLAN START | PLAN DURATION | ACTUAL START | ACTUAL DURATION | PERCENT COMPLETE | M | T | W | Th | F | S | Su | M | T | W | Th | F | S | Su | M | T | W | Th | F | S | Su | M | T | W | Th | F | S | Su | M | T | W | Th | F | S | Su | M | T | W | Th | F | S | Su | M | T | W | Th | F | S | Su | M | T | W | Th | F | S | Su | M | T | W | Th | F | S | Su | M | T | W | Th | F | S | Su | M | T | W | Th | F | S | Su | M | T | W | Th | F | S | Su | M | T | W | Th | F | S | Su | M | T | W | Th | F | S | Su | M | T | W | Th | F | S | Su | M | T | W | Th | F | S | Su | M | T | W | Th | F | S | Su
[7 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 79 | 80 | 81 | 82 | 83 | 84 | 85 | 86 | 87 | 88 | 89 | 90 | 91 | 92 | 93 | 94 | 95 | 96 | 97 | 98 | 99 | 100 | 101 | 102 | 103 | 104 | 105 | 106 | 107 | 108 | 109 | 110 | 111 | 112 | 113 | 114 | 115 | 116 | 117 | 118 | 119
| Project | 1 | 114 | 1 | 114 | 47%
| Hiring & Picking a Project | 1 | 6 | 1 | 6 | 100%
| The Engineering Method | 9 | 14 | 9 | 14 | 100%
| Developing the Task Matrix | 23 | 14 | 23 | 14 | 100%
| Mission Objective & Level 1 Requirements | 18 | 8 | 18 | 8 | 100%
| Systems | 37 | 73 | 37 | 73 | 24%
1.0 - Project
| 1.1.1 - Hex Planning & Schedule | 32 | 13 | 32 | 13 | 100%
| 1.2.1 - Hex Preliminary Budgets | 30 | 8 | 30 | 8 | 100%
| 1.3.1 - Hex Preliminary Blog Post Review | Done | Done | Done | Done
| 1.4.2.1 - Hex L1 & L2 Requirements | 30 | 8 | 30 | 8 | 100%
| 1.5.1 - Hex Verfication Plans | 38 | 7 | 38 | 7 | 100%
| 1.6.1 - Hex Final Blog Post | 99 | 8 | 99 | 8 | 0%
| 1.7.1 - Hex Project Video | 102 | 12 | 102 | 12 | 0%
| System block diagram | 39 | 8 | 39 | 8 | 100%
| Work Breakdown Structure | 39 | 8 | 39 | 8 | 100%
| Product Breakdown Structure | 39 | 8 | 39 | 8 | 100%
| Interface Matrix | 39 | 8 | 39 | 8 | 100%
| Prototype Fritzing Diagram | 39 | 8 | 39 | 8 | 100%
| Resource Reports | 39 | 8 | 39 | 8 | 100%
| Mechanical Drawing | 39 | 8 | 39 | 8 | 100%
2.0 - Misson Plan
| 2.1.1 - Rules of the Game | N/A | N/A | N/A | N/A | 0%
| 2.1.2 - Maze Definition | 33 | 7 | 33 | 7 | 100%
| 2.2 - Robot Avoidance Rules/Strategy - Part I & II | N/A | N/A | N/A | N/A | 0%
| 2.4.1 - Hex Additional Robot Specific Mission | 38 | 7 | 38 | 7 | 100%
3.0 - Resources
| 3.1.1 - Generic Power Template | 39 | 8 | 39 | 8 | 100%
| 3.1.2.1 - Hex Project Power Budgets & Tracking | 39 | 8 | 39 | 8 | 100%
| 3.1.3.1 - Micrometal Power Estimates | 38 | 7 | 38 | 7 | 100%
| 3.1.4.1 - Hex Mock-up With Motor Power under Load | 38 | 7 | 38 | 14 | 100%
| 3.1.6.6 - UV Sensors | 39 | 8 | 39 | 13 | 100%
| 3.2.1 - Hex 3D Print Time | 44 | 8 | 44 | 10 | 100%
| 3.3.1 - Hex Mass (Preliminary & Final) | 44 | 8 | 44 | 8 | 100%
| 3.4.1 - Hex Cable Tree & Assembly Diagram | 46 | 15 | 46 | 15 | 55%
| 4.0 - Hardware | 37 | 73 | 37 | 73 | 24%
4.0 - Hardware
| 4.1.1.1.1 - Decision on Motor Type | 33 | 7 | 33 | 7 | 100%
| 4.1.1.1.3 - UV Sensors Study | 38 | 7 | 38 | 7 | 100%
| 4.1.1.1.4 - RGB Color Sensors | 39 | 8 | 39 | 8 | 100%
| 4.2.3 - v6.43 Testing Debugging 3DoT | TBD | TBD | TBD | TBD | 0%
| 4.3.1 - Breadboard & Schematics - Fritz | 53 | 8 | 53 | 8 | 10%
| Training for Eagle | 53 | 8 | 53 | 8 | 10%
| 4.4.1.1 - Build & Test | 60 | 8 | 60 | 8 | 0%
| 4.4.1.4 - Integration Testing | 67 | 8 | 67 | 8 | 0%
| 4.5.1 - BOM | 65 | 8 | 65 | 8 | 0%
| 4.6.1 - Getting 3DoT David Working | 46 | 8 | 46 | 8 | 100%
| 5 -Programming | 37 | 73 | 37 | 73 | 24%
| 5.2.0 - Labs 1-2 | 37 | 8 | 37 | 8 | 100%
| 5.3.0 - Lab 3 | 44 | 7 | 44 | 7 | 100%
| 5.4.0 - Lab 4-6 | 51 | 7 | 51 | 7 | 50%
| 5.2.1 - Hex Line Follower Code & Demo | 67 | 7 | 67 | 7 | 0%
| 5.3.1 - Hex - Turning Code & Demo | 74 | 7 | 74 | 7 | 0%
| 5.4.1 - Whichway Code & Demo | 81 | 7 | 81 | 7 | 0%
| 5.5.1 - Hex Custom Command Config & Telemetry (APP side) | 79 | 14 | 79 | 14 | 0%
| 5.6.1 - Hexy Code Translating Custom Command Telemetry (Arduino side) | 81 | 14 | 81 | 14 | 0%
| 5.7.1 - Robot Avoidance General Algorithim | 65 | 14 | 65 | 14 | 0%
| 5.7.2.1 - Hexy Detection Code & Demo | 79 | 14 | 79 | 14 | 0%
| 5.7.2.2 - Hexy Action Code & Demo ??? | ?? | 14 | ?? | 14 | 0%
| 5.8.1.1 - Hexy Custom Control Code ???? | 86 | 14 | 86 | 14 | 0%
| 5.9.1 - Hexy Final Arduino Code | 99 | 3 | 99 | 3 | 0%
| 5.10.2 - Integrating 3DoT David Software with Ours | 83 | 2 | 83 | 2 | 0%
| 6.0 - Manufacturing | 37 | 73 | 37 | 73 | 24%
| 6.1.2 - Decision on Movement Mechanism | 38 | 7 | 38 | 7 | 100%
| 6.1.3 - Determining Gear Design | 40 | 7 | 40 | 7 | 100%
| 6.1.4 - Improving 3DoT David Design | 45 | 7 | 45 | 7 | 100%
| 6.1.6 - 3-D Solid Works Model | 45 | 16 | 45 | 16 | 60%
| 6.1.8 Prototype | 61 | 7 | 61 | 7 | 0%
| 6.2.2 - Stress Testing | 61 | 7 | 61 | 7 | 0%
| 6.2.3 - Descision on Picking Materials & Fabrication ???? | 68 | 7 | 68 | 7 | 0%
| 6.2.4 - Manufacturing Prototype | 68 | 7 | 68 | 7 | 0%
| 6.3.1.1 - Revisions | 75 | 14 | 75 | 14 | 0%
| 6.3.1.2 - Final 3-D Model | 89 | 7 | 89 | 7 | 0%
| 6.4.1 - Hex Custom PCB Assembly & Fabrication | 75 | 14 | 75 | 14 | 0%
| 6.5.1 - Hexy Final System Integration & Test | 96 | 7 | 96 | 7 | 0%
| 8.0 Lessons Learned | 0 | 0 | 0 | 0 | 0%
| 8.2 Spider Bot | 99 | 8 | 99 | 8 | 0%
9.0 - Resources Review
| 9.1 Updating 3.0 Resource Content | 99 | 8 | 99 | 8 | 0%