## burndown
Task | start | week 13 | week 12 | week 11 | week 10 | week 9 | week 8 | week 7 | week 6 | week 5 | week 4 | week 3 | week 2 | week 1
Case Studies | 10 | [12 empty] | 10
Prototype Building | 12 | [9 empty] | 10 |  |  | 12
Prototype Testing | 10 | [9 empty] | 10 |  |  | 0
Documentation | 10 | [11 empty] | 5 | 0
Case Study | 10 | [12 empty] | 0
Planning | 20 | [11 empty] | 2 | 0
Order and Manufacture Parts | 20 | [8 empty] | 12 |  | 3 |  | 0
Initial Build | 5 | [7 empty] | 5 |  |  |  |  | 0
prototype test | 20 | [6 empty] | 6 | 2 |  |  |  |  | 0
Documentation | 10 | [5 empty] | 8 | 1 | [5 empty] | 0
Final Build with Finishing | 10 |  |  |  |  | 6 | 3 | [6 empty] | 0
Testing Software | 5 |  |  |  | 3 | 2 | [7 empty] | 0
documentation | 10 |  | 7 | 2 | [9 empty] | 0
Assembly and Test | 2 |  | 5 | [10 empty] | 0
Estimated Hours Remaining | 154 | 142.1538 | 130.3077 | 118.4615 | 106.6154 | 94.7692 | 82.9231 | 71.0769 | 59.2308 | 47.3846 | 35.5385 | 23.6923 | 11.8462 | 0
Actual Hours Remaining | 154 | 132 | 125 | 122 | 102 | 90 | 83 | 76 | 65 | 57 | 54 | 52 | 40 | 40
Precent Completed as of 4/20/2018
79%

## summary
printing | PCB | repaired parts | improved running time | periscope lens | replace switch | organize cables | avoid objects | moving parts risk | figure 8
90 | 90 | 80 | 50 | 50 | 5 | 10 | 10 | 5 | 100