## Verification
Requirement Number | Requirement Text | Verification Success Criteria | Verification Method | Test Case(s) involved
C-11 | All TRC Robots will have 3D components printed in less than 6 hours, with each individual part taking no more than 2 hours to print. | Total print time is less than 6 hours. Each individual part does not exceed 2 hours. | Demonstration | TC-05
L1-1 | 3DoT Hexy shall stop when an obstacle has been detected in front of it. | Object detection is within the specified range (no less than 10 cm and no more than 25 cm at a viewing angle (cone) between 30 degrees and 40 degrees facing forward). 3DoT Hexy robot stops when detecting within those ranges. | Test | TC-03
L1-3 | 3DoT Hexy shall cost no more than $250. | Total cost of the 3DoT project is less than $250. | Analysis | TC-08
L2-3 | 3DoT Hexy shall use (3) IR sensor and (3) IR LEDs) to detect the black lines in the maze (handle intersection detection and for either line following or hedge following). | Test the IR sensors and LED's against the black lines in the maze and confirm detection via code outputs. | Test | TC-03
L2-3 | 3DoT Hexy will use a (3) IR sensors and (3) IR LED's. | Visually inspect 3DoT Hexy and locate the IR sensors and LED's. | Inspection | TC-03
L2-4 | 3DoT Hexy shall use an ultrasonic sensor to detect other robots. | Visually inspect 3DoT Hexy and locate the ultrasonic sensor. | Inspection | TC-06
C-10 | 3DoT Hexy shall pause (turn off motors) when another robot is detected from a distace of no less than 10 cm and no more than 25 cm at a viewing angle (cone) between 30 degrees and 40 degrees facing forward | Test data that shows that 3DoT Hexy can stop when it detects an obstacle in front of it within specified range (allow 5% tolerance). | Test | TC-07
L1-2 | 3DoT Hexy will use 2 micro motors. | Visually ensure that the 3DoT Hexy uses 2 micro motors. | Inspection | TC-06
C-06 | All TRC robots will be controlled via the Arxrobot app | 3DoT Hexy responds to commands from the Arxrobot app. | Test | TC-01
C-01 | All The Robot Company (TRC) Robots shall be completed by May 15, 2018 | 3DoT Hexy is completed by May 15, 2018 | Demonstration, Inspection
C-03 | All TRC Robots will be designed to be a toy robot for people ages 8+ | The robot can perform basic movement functions (forward, right/left turns). | Inspection, Demonstration | TC-01
C-12 | All TRC Robots shall use a 3DoT board. | 3DoT is the microcontroller used for the toy robot. | Inspection | TC-01
C-07 | The robot will need to navigate remotely through a custom-built maze (built by AoSa image), memorize the path it took, and autonomously travel through the path it took. | 3DoT Hexy navigates the maze remotely and the second time autonomously. | Demonstration, Test | TC-02
C-05 | ALL TRC Robots shall be disassembled in 10 minutes | All components disassembled: no wires connected to 3DoT, disassemble chassis, disconnect all sensors. | Test | TC-06
C-04 | All TRC Robots shall be assembled in 10 minutes. | All components reassembled and basic movement commands are tested. | Test | TC-06
L1-4 | 3DoT shall have a custom PCB as platform to build from and incorporate peripherals for sensors. | Custom PCB houses an 4-channel I2C expander and has connections for sensors and other peripherals. Custom PCB works as intended. | Inspection | TC-03
C-08 | Video support during autonomous navigation will be provided via the Arxterra control panel. | Live video feedback from a smartphone via the Arxterra control panel. | Demonstration | TC-04
C-15 | The robot shall incorporate 3D printed parts to demonstrate the feasibility of the 3DoT board for 3D printed robots. | The robot uses 3D printed chassis, legs and a hardware cover. | Inspection | TC-05
L1-6 | 3DoT Hexy will weigh no more than 450 grams. | Delivered final 3DoT Hexy robot weighs less than 450 grams. | Test | TC-08

## 4.1 TC-01 3DoT Board operation
4.11 Detailed Description | This case will help verify communication to the 3DoT Robotics microcontroller board from the Smartphone ArxRobot app. 3DoT Hexy will need to respond to movement commands from the ArxRobot application, as this will be the main form of navigation throughout the maze.
4.1.2 TC-01 3DoT Board operation with remote control via smartphone
Requirement Number | Description | Success Criteria | Verification Method | Procedure Step Results | Pass/Fail
C-06 | All TRC Robots will be able to be controlled through the ArxRobot application via Bluetooth. (add turning radius)Arterra commands robot to turn. | 3DoT Hexy responds to commands from the ArxRobot application | Test | 1 | Pass
C-03 | All TRC Robots will be designed to be a toy robot for people ages 8+ | The robot can perform basic movement functions (line following, right/left turns) | Inspection, Demonstration | 1 | Pass
C-12 | The robot shall use a v6.43a 3DoT board. | 3DoT Hexy uses a v6.43 3DoT board to operate | Inspection | 2 | Waived
4.1.3 Detailed Success Criteria | 3DoT Hexy will need to connect to the ArxRobot app and receive and execute commands from the ArxRobot application GUI (graphical user interface). These commands are: left turn, right turn, turn around and forward.
4.1.4 Test Environment | The test environment requires the completed 3DoT Hexy spiderbot, a smartphone with the ArxRobot application installed, and the presence of the customer. Test should be conducted indoors on a flat surface.
4.1.5 Assumptions and Preconditions | ● 3DoT Hexy is complete and assembled. | ● A location indoors with a flat surface for testing.

## 4.1.6 TC-01 Steps
4.1.6 TC-01 3DoT Arxterra Testing Test Steps
Step Number | Description | Pass Criteria | Recorded Data? | Linked Requirement | Test Method
1 | Connect the 3DoT Hexy toy robot to the ArxRobot application. Issue simple move commands to verify communication between the toy robot and the 3DoT board using the Arxrobot app. Custom command for red LEDs to turn on, perform a left turn and succesfully go foward as second step. | 3DoT Hexy responds to movement commands from ArxRobot application. Red LEDs on, left turn with turning radius xx, and forward movement as second step. | Appendix xx | C-06, C-03 | Test
2 | The robot uses a v6.43a 3DoT board. | 3DoT Hexy uses a v6.43a 3DoT board to operate/function | N/A | C-12 | Inspection

## 4.2 TC-02 Navigation
4.21 Detailed Description | This test will help verify that 3DoT Hexy is able to complete the maze navigation.
4.2.2 TC-02 Navigation
Requirement Number | Description | Success Criteria | Verification Method | Procedure Step Results | Pass/Fail
C-07 | The robot will need to navigate remotely through a custom-built maze (built by AoSa image), memorize the path it took, and autonomously travel through the path it took. | 3DoT Hexy navigates the maze remotely and the second time autonomously. | Demonstration, Test | 1
4.2.3 Detailed Success Criteria | Success is defined with the robot being able to complete the maze with guided control and autonomous navigation of the maze.
4.2.4 Test Environment | The test environment requires the completed 3DoT Hexy spiderbot, a smartphone with the ArxRobot application installed, and the presence of the customer. Test should be conducted indoors on the maze placed on a flat surface.
4.2.5 Assumptions and Preconditions | ● 3DoT Hexy is complete and assembled. | ● A location indoors with a flat surface for testing. (Maze is available)

## 4.2.6 TC-02 Steps
4.2.6 TC-02 Navigation Test Steps
Step Number | Description | Pass Criteria | Recorded Data? | Linked Requirement | Test Method
1 | This test will help verify that 3DoT Hexy is able to complete the maze navigation. | The robot being able to complete the maze with guided control and autonomous navigation of the maze. | N/A | C-07 | Demonstration, Test

## 4.3 TC-03 Sensor Testing
4.3.1 Detailed Description | These tests deal with the light sensors and IR LEDs. These tests are to verify that the sensors used in the 3DoT Hexy project are functioning as intended. The light sensors will read reflected light from the IR LEDs to detect black lines in the maze (line follower) and assist in intersection detection. A custom PCB is used to incorporate peripherals for all sensors used in this project.
4.3.2 TC-03 Sensor Testing
Requirement Number | Description | Success Criteria | Verification Method | Procedure Step Results | Pass/Fail
L2-3 | 3DoT Hexy shall use three light sensors with three IR LEDs to detect the black lines in the maze. | Test light sensors against the black lines in the maze and confirm detection via code outputs. | Test | 1 | Pass
L1-4 | 3DoT shall have a custom PCB as platform to build from and incorporate peripherals for sensors. | Custom PCB houses an 4-channel I2C expander and has connections for sensors and other peripherals. Custom PCB works as intended. | Inspection | 2
4.3.3 Detailed Success Criteria | The robot shal use the light sensors along with IR LEDs to detect the black lines in the maze. A custom PCB is used incorporate peripherals for sensors (ultrasonic, IR LEDS, two red LEDS).
4.3.4 Test Environment | The test environment is to have the maze placed on a flat surface.
4.3.5 Assumptions and Preconditions | ● 3DoT Hexy is complete and assembled. | ● Line following can be tested through inspection and test data. Both are given for this test. | ● Custom PCB is assembled

## 4.3.6 TC-03 Steps
4.3.6 TC-03 Sensor Testing Test Steps
Step Number | Description | Pass Criteria | Recorded Data? | Linked Requirement | Test Method
1 | The E&C engineer set up code to test Light sensors with IR LEDs on black lines of the maze. | 3DoT Hexy can stay distinguish lines of the maze (black, white and green). Confirm detection via code outputs. | Appendix xx | L1-1, L2-3 | Test
2 | 3DoT Hexy uses a custom PCB as platform to build from and incorporate peripherals for sensors. | 3DoT Hexy operates using the custom sensor PCB. |  | L1-4 | Inspection

## 4.4 TC-04 Arxterra Control Pane
4.41 Detailed Description | This case will help verify communication to the 3DoT Robotics microcontroller board from the Arxterra Control Panel. 3DoT Hexy will need to provide live video feeback from a smartphone.
4.4.2 TC-04 Arxterra Control Panel
Requirement Number | Description | Success Criteria | V&V Method | Procedure Step Results | Pass/Fail
C-08 | Video support during autonomous navigation will be provided via the Arxterra control panel. | Live video feedback from a smartphone via the Arxterra control panel. | Demonstration | 1
4.4.3 Detailed Success Criteria | 3DoT Hexy will need to connect to the Arxterra control panel and provide live video feedback from a smartphone.
4.4.4 Test Environment | The test environment requires the completed 3DoT Hexy spiderbot, a smartphone, PC/Laptop with Arxterra control panel, and the presence of the customer. Test should be conducted indoors on a flat surface.
4.4.5 Assumptions and Preconditions | ● 3DoT Hexy is complete and assembled. | ● A location indoors with a flat surface for testing. | ●Smartphone has a camera and has ArxRobot application installed

## 4.4.1 TC-04 Arxterra Control Pa
4.4.6 TC-04 Arxterra Control Panel
Step Number | Description | Pass Criteria | Recorded Data? | Linked Requirement | Test Method
1 | Connect the 3DoT Hexy toy robot to the Arxterra control panel. Have the MST engineer use the Arxterra control panel to see the phone camera output | Demonstration of Arxterra Control Panel live video feed from the phone | Appendix xx | C-08 | Demonstration

## 4.5 TC-05 3D Printing
4.5.1 Detailed Description | These tests verify the 3D print times of 3DoT Hexy and that it meets design requirements. Verify that all 3D print models are printed in good quality and done in less than 6 hours with no individual part taking longer than 2 hours to print (2/2/2/ 6 rule). The 2/2/2 6 Rule (previous limitation) on the print time for parts and material (i.e., PLA) do not apply to the final 3D print.
4.5.2 TC-05 3D Printing
Requirement Number | Description | Success Criteria | Verification Method | Procedure Step Results | Pass/Fail
C-11 | All TRC Robots will have 3D components printed in less than 6 hours, with each individual part taking no more than 2 hours to print. | Total print time is less than 6 hours (360 minutes). Each individual part does not exceed 2 hours (120 minutes). Waivers can be submitted to approve additional time. | Demonstration | 1 | Waived
C-15 | The robot shall incorporate 3D printed parts to demonstrate the feasibility of the 3DoT board for 3D printed robots. | The robot uses 3D printed chassis, legs and a hardware cover. | Inspection | 2 | Pass
L1-5 | The robot shall have a chassis large enough to house a 3x7 cm 3DoT board. | Top chassis is able to house 3DoT board and top cover fits above the board. | Inspection | 2 | Pass
4.5.3 Detailed Success Criteria | 3D print times meet the requirements set by the customer. Documentation is to be provided to reinforce validity of 3D print times. 3D printed parts meet design requirements (i.e., hardware cover is able to house a 3DoT board). Waiver may be submitted for extension of 3D print times.
4.5.4 Test Environment | No requirements for the test environment
4.5.5 Assumptions and Preconditions | N/A

## 4.5.6 TC-05 Steps
4.5.6 TC-05 3D Printing
Step Number | Description | Pass Criteria | Recorded Data? | Linked Requirement | Test Method
1 | The Manufacturing engineer's design show the print times of each 3D printed component. A spreadsheet is provided with details on the 3D print using services of Ridwan. | Spreadsheet verifies that each part takes dos not exced over 2 hours to 3D print. The total 3D print time of all components is less than 6 hours. Waiver is submitted to approve exceeding time limit. |  | C-11 | Analysis
2 | Visually inspect that 3DoT Hexy's 3D print components include a bottom chassis, (6) legs attached to femur/joints, and a top cover. | 3DoT Hexy incorporates 3D printed parts listed in the design specicifications. Each part is used as intended (i.e., hardware cover houses 3DoT board). |  | C15, L1-5, L2-9 | Inspection

## 4.6 Assembly, Disassembly
4.6.1 Detailed Description | This case will help verify that the 3DoT Hexy can be constructed from subassemblies within 10 minutes and disassembled within 10 minutes. This test case includes verification of all physical parts as well as wire management techniques to make sure all wires used for the project are not dangling or exposed.
4.6.2 TC-06 Assembly and Diassembly
Requirement Number | Description | Success Criteria | Verification Method | Procedure Step Results | Pass/Fail
C-04 | In order to minimize manufacturing and packaging cost, the robot shall be able to be constructed from subassemblies within 10 minutes. | Attach all electronics and mechaincal parts. Assemble robot within 10 minutes | Test | 1
C-05 | For simplicity, disassembly of the robot shall be 10 minutes. | All electronics disconnected from the 3Dot board and custom PCB. Top plate removed with sensors and motors in place. Diassemble robot within 10 minutes. | Test | 2
C-14 | The robot will be designed in such a way that there are no dangling or exposed wires. | No wires are not dangling or exposed. | Inspection | 3 | Pass
C-16 | For good construction techniques, all moving parts and rotating parts will use bushings or bearings. | The gear system uses bearings to operate. | Inspection | 3 | Pass
L2-4 | 3DoT Hexy shall use an ultrasonic sensor to detect other robots. | Visually inspect 3DoT Hexy and locate the ultrasonic sensor. | Inspection | 3 | Pass
L1-2 | To keep cost down, and keep as a toy aspect, the robot will use only 2 micro motors to drive the movement of the robot. | 3DoT Hexy operates using two motors. | Inspection | 3 | Pass
4.6.3 Detailed Success Criteria | Success is defined with the robot using all physical components as intended (i.e., Ultrasonic sensor to detect non-navigable and navigable objects). The robot’s wires are correctly routed through the bottom and top chassis without any dangling or exposed wires. The 3Dot board and custom sensor PCB will be clear of electronics, motors will be disconnected, all sensors will be disconnected. The robot can be assembled within 10 minutes and disassembled within 10 minutes.
4.6.4 Test Environment | Indoor environment with a table to lay parts and tools needed include a philips screwdriver, hex key set and a timer.
4.6.5 Assumptions and Preconditions | ● 3DoT Hexy is complete and assembled. | ● Tools are available (philips screwdriver, hex key set and a timer).

## 4.6.6 Steps
4.6.6 TC-06 Assembly and Diassembly
Step Number | Description | Pass Criteria | Recorded Data? | Linked Requirement | Test Method
1 | Connect all electronics connected to the 3Dot board which include motors, ultrasonic sensor, light sensors (x3), IR LEDs (x3), and red LEDs(x2). Attach legs and top plate. | All electronics and mechaincal parts are configured as intended. Assemble robot within 10 minutes. | Appendix xx | C-04 | Test
2 | Top cover is easily taken off. Legs can be disconnected from the gear system. All electronics disconnected from the 3Dot board and custom PCB. | All electronics disconnected from the 3Dot board and custom PCB. Top plate removed with sensors and motors in place. Diassemble robot within 10 minutes. | Appendix xx | C-05 | Test
3 | Visually inspect the robot for no dangling or exposed wires, an ultrasonic sensor, and that the robot only uses 2 micro motors. Inspect that all moving parts and rotating parts use bearings. | 3DoT Hexy uses an ultrasonic sensor. 3DoT Hexy operates using two motors. 3DoT Hexy has no wires exposed or dangling. The gear system uses bearings to operate. | N/A | C-16, L2-4, L1-2 | Inspection

## 4.7 TC-07 Detecting Obstacles
4.7.1 Detailed Description | This case will help verify that the 3DoT Hexy can detect non-navigable and navigable obstacles at a distance of no less than 10 cm and no more than 25 cm at a viewing angle (cone) between 30 degrees and 40 degrees facing forward. Once 3DoT Hexy detects an obstacle (i.e., other robots), it should stop and continue walking when the obstacle is removed. 3DoT Hexy will use two red LEDs acting as eyes of the robot to indicate that an object is detected.
4.7.2 TC-07 Detecting Non-Navigable and Navigable Obstacles
Requirement Number | Description | Success Criteria | Verification Method | Procedure Step Results | Pass/Fail
C-10 | 3DoT Hexy shall detect non-navigatable and navigable obstacles(i.e., other robots) that are in front of the robot. | Object detection is within the specified range (10cm-25cm), Test the proximity of Ultrasonic sensor to verify that it detects objects | Test | 1 | Pass
C-10 | 3DoT Hexy shall pause (cease motor functions) when an obstacle is detected | Move an object in front of the robot to ensure reliability | Test | 1 | Pass
L2-10 | 3DoT Hexy shall turn on two red LEDs acting as eyes of the robot to indicate that an object is detected | Both LEDs turn on when an obstacle is detected | Test | 1 | Pass
4.7.3 Detailed Success Criteria | To be successful in these tests, the the ultrasonic sensor must sense non-navigable and navigable obstacles at a distance of no less than 10 cm and no more than 25 cm at a viewing angle (cone) between 30 degrees and 40 degrees facing forward. When detecting obstacles, 3DoT Hexy will cease motor functions and also turn on two red LEDs.
4.7.4 Test Environment | The test environment is to have the maze placed on a flat surface.
4.7.5 Assumptions and Preconditions | ● 3DoT Hexy is complete and assembled. | 2. Detection of non-navigable and navigable obstacles can be tested through inspection and test data.

## 4.7.1 TC-07 Steps
4.7.6 TC-07 Detecting Obstacles Test Steps
Step Number | Description | Pass Criteria | Recorded Data? | Linked Requirement | Test Method
1 | The E&C engineer set up code to test the range of the ultrasonic sensor. 3DoT Hexy interacts with different objects at the defined range. 3DoT Hexy stops when an object is detected. Apart from stopping, two red LEDs are turned on to confirm detection of an obstacle. The results can be seen in the test output data. | The ultrasonic sensor detect obstacles at a distance of no less than 10 cm and no more than 25 cm at a viewing angle (cone) between 30 degrees and 40 degrees facing forward. 3DoT Hexy stops when it detects objects and two red LEDs turn on. | Appendix xx | C-10, L2-10 | Test

## 4.8 Final Cost, Weight
4.8.1 Detailed Description | This case will help verify 3DoT Hexy's final cost and weight stays within the allocated budget ($250) and weight limit (450 grams).
4.8.2 TC-08 Final Cost, Weight
Requirement Number | Description | Success Criteria | Verification Method | Procedure Step Results | Pass/Fail
L1-6 | 3DoT Hexy will weigh no more than 450 grams. | Delivered final 3DoT Hexy robot weighs less than 450 grams. | Test | 1 | Pass
L1-3 | 3DoT Hexy will cost no more than $250. | Total project cost is under $250. | Analysis | 2 | Pass/Waived
4.5.3 Detailed Success Criteria | 3DoT Hexy total weight must be under 450 grams as defined in the project specific requirement. The final cost of the project is to be under the budget of $250 and all receipts documented.
4.5.4 Test Environment | Weigh on scale
4.5.5 Assumptions and Preconditions | N/A

## 4.8.6 Steps
4.8.6 TC-08 Final Cost, Weight
Step Number | Description | Pass Criteria | Recorded Data? | Linked Requirement | Test Method
1 | 3DoT Hexy weighed with all is components. | 3DoT Hexy's total weight does not exceed 450 grams. | Appendix xx | L1-6 | Test
2 | Gather up all the receipts for this project and tally them up. Project total cost is ($) | Total cost of the project must not exceed $250 | Appendix xx | L1-3 | Analysis